## Sheet1
ID	Header	Description	Discovered in sprint	Status
5000	System that reigsters energy usage	Find a way to be able to check what has happened during the last "1 seconds of playtime in regards to energy usage" so we know if we can credit player more energy or not	5
5001	Implement sprint 6	I decided to skip sprint 6 for the moment and instead focusing on adding new functionality, new enemies, more areneas etc since sprint 6 didn't feel large enough and important enough at that time	5
5002	Create a new enemy [ranged marine]	Create a new kind of enemy, [ranged marine] it should advance towards player, when a decent distance from player it should fire some shots then continue walking after that	7	13-03-01
5003	Make a faster melee attacker	Like the regular guy but faster and with another attack type	7	13-03-01
5004	Try using Unity as 3D-engine	Skip XNA gogo unity	7	13-03-01
5005	refaktorisera grafik och sådant till 2D-View	Gör om spelaren så den har en View också, likaså fiender. Vyn ska ta in "modellen" som attribut vid draw och därifrån hämta information som den behöver i stil med position, time in state, state osv...	7
5006	fixa in en 3D-view	Vyn ska ta in en modell som information precis som 2d-vyn	7
5007	Förändra rörelser och grundläggande funktionalitet till att inte finnas i "basklassen" utan snarare vara "beteenden" som modulärt kopplas på	Detta upptäcktes i stil med att jag skulel skapa olika fiender, då märkte jag att det var svårt och dumt att bygga på beteendet i en basklass och sedan extenda detta i olika subklasser, det verkar smartare att modulärt trycka på detta iom composites istället för arv som nu	7	13-03-01
5008	Gör så att range-fienden inte kolliderar och vandrar igenom väggen	I och med fiendens AttackBehaviour där den cirkulerar runt spelaren så blev det möjligt för fienden att röra sig igenom väggen. Extrahera boundary-checken till en modul och applicera denna på range-fienden under tiden som den finns i ett AttackBehaviour	7	13-03-01
5009	Add notification when RMB wpn is ready	Need some kind of notification whenever the player can use his secondary weapon. This should only affect the "total time" and not any energy use
5010	Randomize melee movement	Want to do some kind of randomness for melee movement so not EVERYONE always walks straight towards the player
5011	Make enemy shots disintegrate after time/distance	Andreas suggested that shots disintegrate over time to fallout, makes it better for circle strafing enemies and shooting
5012	Make it possible to die	Make sure to add "GodMode"-setting
5013	Create the new boss	Level5 should be a boss level, basic idea. Standing still, attacking with "shot waves" in random circle in front of him and then shooting "missiles/rockets/air strikes" that targets one area close to the player and will land there after a while (similar to the effect found in Secret World)
5014	Scrolling combat text	Sprint planning - Implement Sprint7
5015	Add highscore list	Add highscore for "total points" as well as "individual score each level"
5016	Create "turbo mode"	Make it possible to really speed up the game with some button